### Group 1

* **T1** - Database Structure - n/a: *4hr  
  Michael, Davis*
* **T2** - Device Authentication - t1: *3hr  
  Davis*
* **T3** - Account Authentication - t1, t2: *4hr  
  Davis, John, Michael*
* **T4** - Account Creation / Editing - t3: *5hr  
  Davis, John, Michael*
* **T5** - Sign children in / out - t4: *6hr  
  Davis, John, Michael*
* **T6** - Adding Notes / Reminders - t4: *5hr  
  Davis, John*
* **T7** - Moving Children - t4: *3hr  
  Michael*
* **T8** - News Feed - t4: *3hr  
  John, Michael*
* **T9** - Child List / Info view - t4: *5hr  
  John, Michael*
* **T10** -Name Search - t9: *3hr  
  Davis, Michael*
* **T11** - Parent / Staff contact - t9: *2hr  
  Michael, John*
* **T12** - Parent Interface - t6, t8, t10: *4hr  
  John*
* **T13** - Admin Interface - t6, t8, t10, t11: *4hr  
  John, Michael*
* **T14** - Teacher Interface - t6, t8, t10, t11: *4hr  
  Davis***Project Plan total hours:** *55 total hours + 50% contingency =* ***82.5 hours***